## Daily Status Report
Project | Track | Key | Summary | Issue Type | Assignee | Estimated Hours | Actual Hours [Logged in JIRA] | Start Date | Estimated End Date | Actual End Date | Completion % | What Done Today | What is for Tomorrow | Road Blocks if any
Small Group Renewals | Data |  | Retrive the data from MRDB using Spring Framework | Analysis Development | Gayatri |  | 5hr | 2018-04-05 |  | 2018-04-06 | 70% | <4/6>Is been insisted by Durga to hold this task. <4/5>Identified the process to call a store procedure with out table details . | complete the coding & Junit testcases. NA | NO
Small Group Renewals | Data |  | Workspace setup integration of SearchQuery code with XML retrieving project | Sub-task | Prabhakar |  | 5hr | 2018-04-05 |  | 2018-04-06 | 80% | <4/6> The code is getting built successfully but unable to retrieve the data into the POJOS created by us. <4/5>Integration of the current workspace setup with the workspace setup shared by durga in github .Integrated the code . | Based on the input given by Durga ,will continue to work on the integration. | The structure of the available project in github is different than the existing project The POJOS created by us are different than the POJOS existing .Already been informed to Durga in the coordination call..
Note on O3: Nanduri Gayatri: Red color font is the road block which is yet to be resolved.
Note on O4: Nanduri Gayatri: Red colour font is the road block which is yet to be resolved.